## Sheet1
Project Risks
Design | Initial risk | Current risk | Art | Initial risk | Current risk
Mathmaticals quesiton are at the right level for our chosen age group | Red |  | Ensuring key Stage 2 students engage with the chosen theme | Amber
Our game idea hits the required brief | Amber |  | Making sure art work is created in a modular format | Red
The game has high replayability | Red |  | Creating animations for characters & vehicles | Red
Deciding on type of sounds we want in the game | Amber |  | Ensuring our characters and vechicles appeal to both the male & female demographic | Red
Picking what type of vechicles for characters to race in | Red
Being able to playtest our game on our target demographic | Amber
Programming | Initial risk | Current risk
Having a Ai opponent or timed race | Red
Implementing sounds into the game | Amber
Insuring when it’s a division question there are no remainders | Red
Making sure questions are all random based on set parameters | Red
Insuring the same question cannot occur twice in a row | Red
Red
Amber
Green